## Story Tracker
Story ID | Epic | Story Title | Status | Test Written Date | Test Written Commit | Test Passed Date | Test Passed Commit | Notes
US-1.1 | Epic 1: Artwork Listing & Product Page | Create Listing | Passed | 2026-05-09 | 2e0fc35 | 2026-05-09 |  | 6 tests passing
US-1.2 | Epic 1: Artwork Listing & Product Page | Upload Images | Passed | 2026-05-09 | 2e0fc35 | 2026-05-09 |  | 9 tests passing
US-1.3 | Epic 1: Artwork Listing & Product Page | Add Artwork Details | Passed | 2026-05-09 | 2e0fc35 | 2026-05-09 |  | 4 tests passing
US-1.4 | Epic 1: Artwork Listing & Product Page | Choose Sale Type | Passed | 2026-05-09 | 2e0fc35 | 2026-05-09 |  | 5 tests passing
US-1.5 | Epic 1: Artwork Listing & Product Page | Edit Listing | Passed | 2026-05-09 | 2e0fc35 | 2026-05-09 |  | 5 tests passing
US-1.6 | Epic 1: Artwork Listing & Product Page | Remove Listing | Passed | 2026-05-09 | 2e0fc35 | 2026-05-09 |  | 5 tests passing
US-2.1 | Epic 2: Fixed-Price Sales | Set Price | Passed
US-2.2 | Epic 2: Fixed-Price Sales | View Price | Passed
US-2.3 | Epic 2: Fixed-Price Sales | Buy Now | Passed
US-2.4 | Epic 2: Fixed-Price Sales | Auto-Mark as Sold | Passed
US-3.1 | Epic 3: Auction Sales | Configure Auction | Passed | 2026-05-09 |  | 2026-05-09
US-3.2 | Epic 3: Auction Sales | Place Bid | Passed | 2026-05-09 |  | 2026-05-09
US-3.3 | Epic 3: Auction Sales | View Auction Status | Passed | 2026-05-09 |  | 2026-05-09
US-3.4 | Epic 3: Auction Sales | Outbid Notification | Passed | 2026-05-09 |  | 2026-05-09
US-3.5 | Epic 3: Auction Sales | Auction Close | Passed | 2026-05-09 |  | 2026-05-09
US-3.6 | Epic 3: Auction Sales | Reserve Price Protection | Passed | 2026-05-09 |  | 2026-05-09
US-4.1 | Epic 4: Payments | Pay by Credit Card | Passed
US-4.2 | Epic 4: Payments | Secure Payment Processing | Passed
US-4.3 | Epic 4: Payments | Seller Payouts | Deferred
US-4.4 | Epic 4: Payments | Transaction Records | Passed
US-4.5 | Epic 4: Payments | Purchase Confirmation | Passed
US-5.1 | Epic 5: Tax Calculation | Auto-Calculate Tax by Buyer Location | Not Started
US-5.2 | Epic 5: Tax Calculation | Tax-Exempt Handling | Not Started
US-5.3 | Epic 5: Tax Calculation | Seller Tax Reporting | Not Started
US-5.4 | Epic 5: Tax Calculation | Multi-Currency Display | Not Started
US-6.1 | Epic 6: User Accounts & Auth | Account Creation | Passed | 2026-05-09 | 50ffb73 | 2026-05-09 |  | 13 tests passing
US-6.2 | Epic 6: User Accounts & Auth | Secure Login | Passed | 2026-05-09 | 50ffb73 | 2026-05-09 |  | 7 tests passing
US-6.3 | Epic 6: User Accounts & Auth | Seller Onboarding | Dropped | 2026-05-09 | 50ffb73 | 2026-05-09 |  | 6 tests passing
US-7.1 | Epic 7: Browsing & Discovery | Browse Artwork | Passed
US-7.2 | Epic 7: Browsing & Discovery | Filter & Sort | Passed
US-7.3 | Epic 7: Browsing & Discovery | Search | Passed
US-7.4 | Epic 7: Browsing & Discovery | Unified Artwork Display | Passed
US-8.1 | Epic 8: Print Shop (Prodigi) | Create Print Listing | Passed | 2026-05-09 |  | 2026-05-09
US-8.2 | Epic 8: Print Shop (Prodigi) | Browse Print Options | Passed | 2026-05-09 |  | 2026-05-09
US-8.3 | Epic 8: Print Shop (Prodigi) | Purchase a Print | Passed | 2026-05-09 |  | 2026-05-09
US-8.4 | Epic 8: Print Shop (Prodigi) | Print Order Tracking | Passed | 2026-05-09 |  | 2026-05-09
US-8.5 | Epic 8: Print Shop (Prodigi) | Seller Print Revenue | Passed | 2026-05-09 |  | 2026-05-09
US-8.6 | Epic 8: Print Shop (Prodigi) | Print Quality Assurance | Passed | 2026-05-09 |  | 2026-05-09
US-9.1 | Epic 9: Seller Dashboard & Listing Management | Listings Nav Link | Passed | 2026-05-09 | 9e790dc | 2026-05-09 | 9e790dc | Sellers see 'Listings' link in top nav; admins see 'Admin' link
US-9.2 | Epic 9: Seller Dashboard & Listing Management | Seller Listings Index | Passed | 2026-05-09 | 9e790dc | 2026-05-09 | 9e790dc | Grid of all seller listings with status badge, price, sale type, and action buttons
US-9.3 | Epic 9: Seller Dashboard & Listing Management | Create New Listing | Passed | 2026-05-09 | 9e790dc | 2026-05-09 | 9e790dc | Form to create artwork + fixed-price or auction listing; validates and redirects to edit page
US-9.4 | Epic 9: Seller Dashboard & Listing Management | Edit Listing Details | Passed | 2026-05-09 | 9e790dc | 2026-05-09 | 9e790dc | Pre-populated edit form for title, description, medium, dimensions, year, price/reserve; locked fields on sold/active auctions
US-9.5 | Epic 9: Seller Dashboard & Listing Management | Archive / Activate Listing | Passed | 2026-05-09 | 9e790dc | 2026-05-09 | 9e790dc | Toggle listing between Active and Archived from the listings index; sold listings cannot be toggled
US-9.6 | Epic 9: Seller Dashboard & Listing Management | Admin Project Tracker View | Passed | 2026-05-09 | 9e790dc | 2026-05-09 | 9e790dc | Formatted tracker at /admin/tracker with per-epic progress bars, story status badges, and commit log

## Commit Log
Commit Hash | Date | Author | Stories Affected | Commit Message | Tracker Updated
TBD | 2026-05-09 | Claude Sonnet 4.6 | US-6.1 US-6.2 US-6.3 | feat(epic-6): implement US-6.1 through US-6.3 — user accounts and authentication | Yes
TBD | 2026-05-09 | Claude Sonnet 4.6 | US-1.1 US-1.2 US-1.3 US-1.4 US-1.5 US-1.6 | feat(epic-1): implement US-1.1 through US-1.6 — artwork listing and product page | Yes

## Instructions
PROJECT TRACKER — Instructions
This file MUST be updated with every commit. Commits that do not include a change to this file should be rejected.
STORY TRACKER SHEET
• When you write tests for a user story, update its Status to 'Test Written', fill in 'Test Written Date' and 'Test Written Commit'.
• When you begin implementing code for a story, update its Status to 'In Progress'.
• When all tests for a story pass, update its Status to 'Passed', fill in 'Test Passed Date' and 'Test Passed Commit'.
• Use the Notes column for anything relevant: blockers, partial progress, design decisions.
COMMIT LOG SHEET
• Every commit adds a row: commit hash (short), date, author, which story IDs were affected, and the commit message.
• The 'Tracker Updated' column should always be 'Yes'. If it's ever 'No', the commit should not have been accepted.
STATUS VALUES
• Not Started — No work has begun on this story.
• Test Written — Failing test(s) exist for this story. No implementation yet.
• In Progress — Implementation is underway. Tests are not yet all passing.
• Passed — All tests for this story pass. Implementation is complete.
GIT HOOK ENFORCEMENT
A pre-commit hook should verify that this file (project-tracker.xlsx) has been modified.
If the file is not staged, the commit should be rejected with a message:
"ERROR: project-tracker.xlsx must be updated with every commit. Stage your tracker changes and try again."